## Obligations Register
Obligation ID | Vendor / Supplier | Contract Name / ID | Contract Type | Obligation Category | Obligation / Commitment | Contract Clause / Reference | Trigger Type | Trigger / Milestone | Frequency | Obligation Owner | Vendor Owner / Contact | Supporting Stakeholders | Start Date | Due Date | Reminder Date | Status | Priority / Criticality | Evidence Required | Evidence Link / Location | Last Reviewed | Completion Date | Days to Due | Overdue? | Risk / Impact if Missed | Issue / Remediation Action | Escalation Owner | Notes
OBL-001 | Example Cloud Services Ltd. | MSA-2026-014 | Master Services Agreement | Security / Privacy | Notify the customer of a confirmed security incident within the contractually specified timeframe. | Clause 12.4 | Event-based | Confirmed security incident | As triggered | Security Governance Lead | Supplier Security Contact | Legal; Incident Response |  |  |  | Not Started | Critical | Incident notice and timestamped communication | [5 empty] | Delayed notification may increase regulatory, operational and contractual exposure. | Confirm notification path and test escalation contacts. | CISO delegate | Illustrative example. Replace timeframe with the signed contract requirement.
OBL-002 | Example Facilities Provider | SOW-2026-022 | Statement of Work | Performance / SLA | Submit monthly service performance report and agreed KPI results. | Schedule B, section 3 | Recurring | Monthly reporting cycle | Monthly | Vendor Manager | Supplier Account Manager | Service Owner |  |  |  | In Progress | High | Monthly report; KPI evidence | [5 empty] | Missed reporting can reduce visibility into service performance. | Request report; record issue if not received by the agreed deadline. | Service Owner | Illustrative example.
OBL-003 | Example Business Process Partner | BCP-2026-008 | Services Agreement | Business Continuity | Provide evidence of the annual business continuity test and agreed remediation actions. | Clause 8.2 | Recurring | Annual continuity test | Annually | Business Continuity Lead | Supplier Resilience Contact | Risk; Operations |  |  |  | Not Started | High | Test summary; remediation plan; closure evidence | [5 empty] | Unverified resilience arrangements may affect service continuity. | Review test results and track open actions to closure. | Operational Risk Lead | Illustrative example.
OBL-004 | Example Software Vendor | SaaS-2026-031 | SaaS Agreement | Compliance / Certification | Provide a current security certification or agreed equivalent evidence before expiry of the current certificate. | Exhibit D | Date-based | Certificate renewal | Annual / expiry-based | Third-Party Risk Lead | Supplier Compliance Contact | Information Security |  |  |  | Not Started | High | Current certificate; validation record | [5 empty] | Expired or insufficient evidence may create a control gap. | Request updated evidence and assess any lapse against policy and contract. | TPRM Manager | Illustrative example.
OBL-005 | Example Technology Integrator | TRANS-2026-003 | Transition Agreement | Transition / Exit | Complete knowledge transfer and handover of agreed service documentation at transition milestones. | Exit Schedule, milestone 2 | Milestone-based | Transition milestone 2 | One-time | Service Transition Lead | Supplier Delivery Lead | IT Operations; Procurement |  |  |  | Not Started | Medium | Handover checklist; knowledge-transfer sign-off | [5 empty] | Incomplete handover may disrupt continuity or delay exit. | Confirm acceptance criteria and record accountable approver. | Service Owner | Illustrative example.
Formulas:
Days to Due = IF([Due Date]="","",[Due Date]-TODAY())
Overdue? = IF(OR([Status]="Completed",[Due Date]=""),"",IF([Due Date]<TODAY(),"Overdue","On track"))

## Read Me
CONTRACT OBLIGATIONS TRACKING TEMPLATE
Purpose | A practical register for recording contractual commitments, assigning owners, tracking deadlines, collecting evidence and escalating missed or at-risk obligations.
Important | This is a customizable working template, not legal advice or a substitute for reviewing the executed contract and applicable internal policies. Confirm each obligation, trigger, deadline and evidence requirement against the signed agreement.
Recommended workflow | 1. Review the executed contract and schedules. 2. Record each distinct obligation and exact clause reference. 3. Classify the obligation and trigger. 4. Assign a named internal owner and vendor contact. 5. Enter due dates, recurrence and reminder dates. 6. Define evidence required and acceptance criteria. 7. Review status on an agreed cadence. 8. Record exceptions, remediation, escalation and closure evidence.
Obligation categories | Examples include SLA/KPI performance, security and privacy, regulatory compliance, insurance/certifications, audit/reporting, payment/pricing, continuity and disaster recovery, IP/confidentiality, transition, and termination. Adapt categories to your contract and policy.
Trigger types | Date-based: due on a specific date. Recurring: repeats on a defined cadence. Milestone-based: due when a milestone is reached. Event-based: triggered by an event such as an incident, material change or regulatory update. At renewal/termination: tied to lifecycle events.
Status definitions | Not Started: not yet underway. In Progress: work underway. Awaiting Vendor: supplier action/evidence is pending. Blocked: cannot progress. Completed: evidence reviewed and accepted. Accepted Risk: formally approved exception with owner and review date recorded in Notes or remediation fields. Cancelled: confirmed no longer applicable, with rationale documented.
Evidence and closure | Do not mark an obligation Completed merely because a document was received. Record the evidence location and confirm it meets the contract requirement. For exceptions, document impact, interim controls, accountable approver, remediation deadline and escalation path.
Formula notes | Days to Due and Overdue? are formula-driven using the Due Date and current date. Check that date fields are maintained. Overdue status is a prompt for review, not a legal determination of breach.
Privacy and security | Avoid placing sensitive contract text, personal data or confidential attachments directly in this workbook. Store approved links to access-controlled repositories instead.
Source alignment | Framework informed by Enlighta’s “Beyond SLAs: The Role of Obligations Management for Vendor Contracts” and “Enlighta Continuous TPRM and Strategic Vendor Governance - April 2026”. The sources emphasize obligations beyond SLAs, defined ownership, deadlines/reminders, evidence, contract compliance, continuity, transition, and ongoing governance.