## Read Me
Enlighta Vendor SLA Tracking Template
What this workbook is:
A practical register for recording vendor service-level commitments, actual results, statuses, exceptions, owners and corrective actions.
How to use it:
1. Replace the example rows in the SLA Register sheet with the SLAs from your own contracts.
2. Record the metric definition and measurement method exactly as agreed in the contract.
3. Enter actual results each measurement period and set the Status using the dropdown.
4. Document exceptions, assign a corrective action owner, and set due dates.
5. Track resolution dates and evidence links so reviews remain auditable.
Status values: Met / At Risk / Breached / Under Review / Not Started
Important: This workbook is a tracking aid. It does not determine whether a contractual breach has occurred.
Always validate results against the executed contract's definitions, exclusions and remedies with appropriate stakeholders.

## SLA Register
Vendor / Contract | SLA ID | SLA Metric | Definition & Measurement Method | Contractual Target | Measurement Period | Actual Result | Unit | Status | Exception & Business Impact | Action Owner | Corrective Action | Due Date | Resolution Date | Evidence / Review Notes
Acme Cloud Services / MSA-2024 | SLA-001 | Service availability | Eligible available service time divided by eligible total service time, per MSA Schedule B (excludes agreed maintenance windows) | >= 99.9% | Oct 2026 | 99.87 | % | Breached | Validated result below target; minor customer impact | J. Rivera | Root-cause review with vendor; remediation plan agreed | 2026-11-10 |  | Vendor report + monitoring export
Acme Cloud Services / MSA-2024 | SLA-002 | Critical incident response time | Elapsed time from contractually defined start event to qualifying response (Severity 1) | <= 30 min | Oct 2026 | 24 | min (avg) | Met | [5 empty] | Ticketing export
Northwind BPO / SOW-118 | SLA-014 | Processing accuracy | Correctly processed eligible transactions divided by total eligible transactions | >= 99% | Q3 2026 | 99.2 | % | Met | [5 empty] | Monthly ops report
Northwind BPO / SOW-118 | SLA-015 | Scheduled report delivery | Required reports delivered by agreed deadline | 100% on time | Q3 2026 | 92 | % | Under Review | Two reports late; exclusion rules being validated | M. Chen | Confirm eligibility rules before classification | 2026-11-05 |  | Email records
Helios IT Support / MSA-331 | SLA-021 | Tickets resolved within target | Eligible tickets resolved within agreed targets / all eligible tickets | >= 95% | Oct 2026 | 93.5 | % | At Risk | Downward trend for third consecutive month | A. Okafor | Performance review scheduled; improvement plan drafted | 2026-11-20 |  | Service desk data
Example rows are illustrative — replace with the targets and definitions from your own contracts.